Terms of Reference

National Consultant – Citizen-Centric Digital Service Design and Implementation

### 1. Background

The E-ffective Governance: Accelerating e-Government and Digital Public Services in Bangladesh project, funded by the European Union and implemented by the British Council and Estonian e-Governance Academy in partnership with the Government of Bangladesh, aims to make public digital services more inclusive, user-friendly, and citizen-responsive.

Under Component 3, the project organises Citizen-Centric e-Service Design (CCeD) and Digital Co-Design Labs bringing together government service owners, citizens, and technical experts to co-create practical improvements to pilot digital public services.

These Labs are followed (subject to government approval) by pilot initiatives that demonstrate how design adjustments can improve access, usability, and trust, accompanied by citizen-awareness activities and evaluation for scale-up.

To support this process, the project seeks to engage a National Consultants with demonstrated expertise in digital service design, co-creation facilitation, and citizen engagement.

### 2. Purpose of the assignment

The consultant will provide technical, facilitation, and advisory support for:

- planning and delivery of Co-Design Labs;

- advising government partners during pilot-implementation phases (where approved);

- supporting citizen-awareness activities; and

- preparing evaluation reports and recommendations for scaling up successful practices.

The consultant will work closely with the British Council team, the international facilitator, and focal points from participating government agencies such as DG Health, the Registrar General’s Office, Local Government Division, Department of Education, or similar.

### 3. Phased scope and key tasks

The assignment will have 4 phased approaches:

Phase 1 – Co-Design Lab (initial commitment)
The contract will initially cover preparation and facilitation of one Co-Design Lab.
Subsequent activities (pilot implementation, citizen awareness, evaluation) will proceed only if the relevant Service-Owner agency formally agrees to pilot service improvements.

A. Co-Design Lab preparation and facilitation (approx. 10 days)

- Support design and logistics of the Lab and coordinate with agency focal points.

- Facilitate group sessions, user-journey mapping, and documentation of results.

- Translate citizen and operator feedback into actionable technical and design recommendations.

- Draft Lab summary report and recommendations for pilot scoping.

Phase 2: Pilot implementation support (approx. 15 days – subject to agency agreement)

- Provide technical and process-design guidance to government counterparts and vendors.

- Support negotiation of pilot scope, milestones, and roles.

- Review implementation progress and identify bottlenecks.

Phase 3: Citizen-engagement and public-awareness activities (approx. 10 days – subject to agency agreement)

- Provide feedback to communication and awareness content highlighting thematic service improvements.

- Deliver workshops for District Policy Forums, youth ambassadors, and CSOs in local communities.

Phase 4: Final report and recommendation (approx. 10 days – subject to agency agreement)

- Gather feedback from users, service operators, and stakeholders.

- Analyse pilot outcomes and lessons learned.

- Prepare a concise recommendations report for replication and scale-up.

### 4. Deliverables

- Workshop preparation notes, facilitation plan, and Co-Design Lab documentation (phase 1).

- Review the Co-Design Lab report and develop the e-service agency specific proposal based on the Co-Design Lab workshop recommendations within the project scope (phase 1).

- Interim pilot-implementation progress review (phase 2).

- Awareness campaign materials review and district workshops (phase 3).

- Document lessons learning and recommendations for scale-up (phase 4)

- Other deliverables, as agreed in advance in writing with the project.

### 5. Duration and level of effort

Estimated total level of effort: 45 working days over a period of six months from November 2025 – April 2026, distributed approximately as follows:

- 10 days – Co-Design Lab preparation and facilitation

- 15 days – Pilot implementation support (conditional)

- 10 days – Citizen engagement and awareness (conditional)

- 10 days – Evaluation and final report (conditional)

Actual days and sequencing will depend on government partner confirmation and activity scheduling.

Estimated start: November 2025

### 6. Payment terms

Payment will be made per actual days worked, based on approved timesheets and deliverables certified by the British Council Team Leader.

### 7. Qualifications and experience

Essential

- At least 10 years of professional experience in digital public-service development, service design, or public-sector innovation.

- Proven experience in facilitating co-design workshops, design sprints, or user-journey mapping.

- Strong record in curriculum development, training delivery, or capacity-building for government professionals.

- Demonstrated collaboration with public institutions in at least one of the following thematic areas: health, identity management, local government services, or education.

- Excellent communication and analytical skills; ability to produce clear reports in English.

Desirable

- Experience with EU-funded or donor-supported governance projects.

- Familiarity with citizen-feedback tools and service-quality standards.

- Fluency in Bangla for field facilitation and documentation.

### 8. Reporting and coordination

The consultant will report to the Team Leader, E-ffective Governance Project, under day-to-day supervision of the Senior Programme Manager.

Coordination with government focal points and British Council technical advisors will be required throughout the assignment.

### 9. Location

Dhaka with possible short field visits to selected pilot districts (e.g., Bagerhat, Kushtia, Nilphamari, or others agreed with government partners).

### 10. Application Process

Interested candidates should submit following documents (pdfs only) at recruitment.nfe@britishcouncil.org and copy to mdshariful.haque1@britishcouncil.org:

- CV(s) highlighting relevant experience.

- Cover letter. Please highlight your expected daily rate in the cover letter.

Please ensure to mark the subject line as “National Consultant - Citizen-Centric Digital Service Design and Implementation.”

Note: No hard copy applications will be accepted. Only shortlisted candidates will be contacted for the next stage of the recruitment process.

Submission deadline: 1 November 2025.